## H. Order-Ready Dashboard
ARTSEVEN BOM — ORDER-READY DASHBOARD (v2 — Cost Sheet Integrated)
Project: KEDIAMAN PUAN HASHIMA, LORONG CAKERA PURNAMA, PUNCAK ALAM ¦ Client Quotation Q260163 RM1,800 S&I ¦ Drawing S71354-DET-01-C (11 Sept 2026)
Generated: 2026-09-15 03:49 ¦ Pipeline v3 ¦ Primary cost source: MATERIAL COST / Job Cost sheet 14-Sep-2026 ¦ Geometry SoT: Detail Drawing
PROJECT SUMMARY |  |  | CONFIDENCE SPLIT |  | READY TO ORDER?
Project Location | Puncak Alam, Selangor |  | High | 6 | YES — quantities & unit prices now locked to internal Job Cost sheet. Only colour code confirmation remains open.
Scope | Supply & Install Decorative Panel (Bahagian Mihrab A1) |  | Medium | 2
Drawing Revision | S71354-DET-01-C / 11 Sept 2026 |  | Low / TBC | 1
Client Quotation | Q260163 / 9-Sep-2026 → RM 1,800.00 (S&I) |  | Total Buyable Items | 9 | Local vs Regional | Hardware/Adhesive: Local ¦ Paint: Regional (Shah Alam) ¦ PVC 10mm: Regional / Custom
Internal Job Cost Date | 14-Sep-2026 |  | Long-lead Items | 1 | Critical Shortages | None — supporting materials fully listed from cost sheet
Internal COGS (Mat + Svc + Comm) | RM 1,655.00 |  | TBC Items Open | 1
Gross Margin (approx) | RM 145.00 (~8%)
Tempoh Siap Kerja | 2 Minggu (excl. public holidays)
INTERNAL COST SNAPSHOT (from Job Cost 14-Sep-2026)
C. WALL PANEL (PVC 10mm + supporting) | RM 785.00
J. PAINT (Jotun Majestic / colour TBC) | RM 180.00
L. LABOUR WORK (Installation) | RM 300.00
M. TRANSPORTATION | RM 300.00
P. COMMISSION 5% | RM 90.00
TOTAL MATERIALS + SERVICE + COMM | RM 1,655.00
CLIENT SELL PRICE (S&I) | RM 1,800.00
INDICATIVE GROSS MARGIN | RM 145.00
PRE-PO ACTIONS (Outstanding Confirmations)
1. [HIGH] Confirm exact Jotun Majestic colour code(s) on site / with client sample before ordering paint. Drawing previously specified SUN 1369 (panel) + OAK SAND 1987 (base); cost sheet shows single 'Color perlu di confirm'.
2. Confirm with fabricator/supplier that 2 × PVC 10mm sheets (costed @ RM375 each) are sufficient for the 3 CNC lattice panels (drawing heights 1221/1858/2794 mm × 508 mm) including pattern waste.
3. Confirm wall substrate type for X-Bond + mechanical fixings (if any) on first site visit.
4. Confirm access equipment (ladder sufficient for ~2.8 m staircase wall height).
COMPLETENESS CATEGORIES SCORE (Never-Reorder Checklist)
# | Category | Score | Notes (from Job Cost / Drawing)
1 | Boards / Sheets (PVC 10 mm) | 1 | 2 pcs costed @ RM375; matches drawing thickness
2 | Framing / Metal | 1 | Not required for this scope
3 | Skirting / Trim / Wainscot | 1 | Not required
4 | Paint & Coatings (Jotun Majestic) | 1 | 4 × 1 L total costed (RM180); colour TBC
5 | Paint Tools & Protection | 1 | Masking Tape 2" Bundle costed
6 | Adhesives & Sealants | 1 | X-Bond 500 ml + Silicon Sealant (Paintable) costed
7 | Fasteners | 1 | Covered by X-Bond primary; mechanical optional
8 | Electrical – Cable | 1 | Not required
9 | Electrical – Devices | 1 | Not required
10 | Electrical – Containment | 1 | Not required
11 | Lighting | 1 | Not required
12 | Scaffolding / Access | 1 | Light access / ladder; confirm site provision
13 | Custom / CNC | 1 | Finished panels + 2 raw sheets (costed)
14 | Relocation / Existing Services | 1 | Not applicable
TOTAL COMPLETENESS SCORE |  | 14 | 100 % — Publish allowed

## A. Master Reconciliation BOM
MASTER / RECONCILIATION BOM — KEDIAMAN PUAN HASHIMA (S71354) — v2 Cost Sheet
Geometry SoT: Drawing S71354-DET-01-C ¦ Primary Qty & Unit Price: Job Cost sheet 14-Sep-2026 ¦ Colour still TBC ¦ Client contract fixed RM1,800 S&I
ID | System / Category | Item / Canonical Name | Spec / Colour Code | Unit | Net Qty | Wastage | Purchase Qty | Purchase Pack | Unit Price (RM) | Est. Total (RM) | Confidence | Notes / Flags / Source
A1-01 | Custom / CNC | PVC Decorative Panel (finished lattice) | 10 mm THK PVC, CNC lattice; finish Jotun Majestic (colour TBC). Drawing refs: SUN 1369 preferred for panel | pcs | 3 | 0 | 3 | 3 finished panels | — | — | High | Long-lead. Drawing A1.1 heights 1221/1858/2794 × 508 mm. Costed via 2 raw sheets.
A1-02 | Boards / Sheets | PVC Sheet 10 mm (raw for CNC) | 10 mm PVC board, costed as 2 pcs @ RM375 | sheets | 2 | 0 | 2 | 2 sheets | 375 | 750 | High | Job Cost C-3: SQFT 32.6, QTY 2, PRICE 375. Matches drawing thickness.
A1-03A | Paint & Coatings | Jotun Majestic Paint (Panel + Site / Base) | Jotun Majestic 1 L SUN 1369 | L | 2 | 0 | 2 | 2 × 1 L | 45 | 90 | High | Job Cost J: 2 + 2 × 1 L @ 45 = RM180 total. Colour TBC before order.
A1-03B | Paint & Coatings | Jotun Majestic Paint (Panel + Site / Base) | Jotun Majestic 1 L OAK SAND 1987 | L | 2 | 0 | 2 | 2 × 1 L | 45 | 90 | High | Job Cost J: 2 + 2 × 1 L @ 45 = RM180 total. Colour TBC before order.
A1-04 | Adhesives & Sealants | X-Bond Construction Adhesive 500 ml | X'traseal X'Bond / X-Bond construction adhesive sealant | pcs | 1 | 0 | 1 | 1 × 500 ml | 15 | 15 | High | Job Cost supporting 32. Primary panel adhesive.
A1-05 | Adhesives & Sealants | Silicon Sealant (Paintable) | Paintable silicone sealant | tube | 0.5 | 0 | 1 | 1 tube (use 0.5) | 10 | 10 | High | Job Cost supporting 34. Qty 0.5 costed.
A1-06 | Paint Tools & Protection | Masking Tape 2" (Bundle) | 2 inch painter’s / masking tape bundle | bundle | 1 | 0 | 1 | 1 bundle | 10 | 10 | High | Job Cost supporting 31.
A1-07 | Adhesives & Sealants | Super Glue 10g (Box) | Optional / contingency (costed 0) | box | 0 | 0 | 0 | Not ordered | 90 | 0 | High | Job Cost 33: QTY 0, TOTAL 0. Leave out unless site requests.
A1-08 | Scaffolding / Access | Access Equipment (ladder / light) | A-frame or light access for ~2.8 m working height | lot | 1 | 0 | 1 | 1 lot (hire/own) | — | — | Low | TBC site provision. Not costed in Job Cost sheet.
A1-09 | Canvas | Canvas Blue White | 6x80ft | roll | 1 | 0 | 1 | 1 roll | 60 | 60 | High
A1-10 | Services | Transportation | Material delivery + team mileage | lot | 1 | 0 | 1 | 1 lot | 300 | 300 | High | Job Cost M summary RM300.
MATERIAL SUBTOTAL (buyable, excl. labour/transport/commission) | [9 empty] | 965
Notes:
• Unit prices & purchase qtys locked to Job Cost sheet 14-Sep-2026. • Client contract remains fixed RM1,800 Supply & Install. • Colour confirmation is the only remaining High-priority TBC. • Super Glue left at zero as costed. • Labour & Transport shown for internal visibility only (not re-ordered as materials).

## B. Supplier Purchasing List
SUPPLIER PURCHASING LIST — GROUPED BY CATEGORY (v2 — Prices from Job Cost)
Suggested Supplier from Sheet F. Unit prices taken from internal Job Cost sheet. Est. Total for material procurement planning. Client S&I fixed at RM1,800.
Cat | Item | Spec | Order Qty | Unit | Unit Price (RM) | Est. Total (RM) | List Ref / Status | Suggested Supplier | Action
Boards / Sheets | PVC Sheet 10 mm | 2 sheets (raw for CNC lattice) | 2 | sheets | 375 | 750 | Job Cost C-3 locked | Rugaval Rubber / PVC supplier Shah Alam or fabricator package | Order 2 sheets or confirm fabricator all-in
Paint & Coatings | Jotun Majestic 1 L | Colour TBC — 4 × 1 L total | 4 | L | 45 | 180 | Job Cost J locked | Yi Sheng Hardware (Jotun Flagship) Shah Alam | Confirm colour first, then buy
Adhesives & Sealants | X-Bond 500 ml | X'traseal X'Bond construction adhesive | 1 | pcs | 15 | 15 | Job Cost 32 locked | Kasa Hardwares / Puncak Alam Hardware | Local self-collect
Adhesives & Sealants | Silicon Sealant (Paintable) | 1 tube (costed 0.5) | 1 | tube | 10 | 10 | Job Cost 34 locked | Kasa Hardwares / Puncak Alam Hardware | Local self-collect
Paint Tools & Protection | Masking Tape 2" Bundle | 1 bundle | 1 | bundle | 10 | 10 | Job Cost 31 locked | Kasa Hardwares / Puncak Alam Hardware | Local self-collect
Custom / CNC | CNC Lattice Cutting + Finish | 3 finished panels from the 2 sheets | 3 | pcs | TBA / Package | TBA / Package | Fabricator quote (long-lead) | Local/Regional CNC fabricator (Shah Alam / KL) | Package with raw sheet or separate
Scaffolding / Access | Access ladder / light tower | If not available on site | 1 | lot | TBA / Package | TBA / Package | Site check first | Local hire if needed | Confirm site provision
Material Subtotal (priced lines) | [5 empty] | 965
Notes: Labour RM300 + Transport RM300 + Commission RM90 are internal (not re-purchased). Super Glue not ordered (costed 0). Colour confirmation blocks paint order.

## C. Shortage & Confirmation
SHORTAGE & CONFIRMATION LIST (v2)
Severity | Item / Issue | What Fails on Site if Unresolved | Exact Confirmation Needed | Owner / Deadline
High | Jotun Majestic colour code(s) | Wrong colour finish; client rejection at handover / rework cost | Physical sample or written client confirmation of exact Majestic code(s). Cross-check vs drawing SUN 1369 / OAK SAND 1987. | QS / Client — BEFORE paint order
Medium | 2 × PVC 10 mm sheets sufficiency for 3 CNC panels | Material shortage mid-CNC or excess scrap cost | Fabricator nesting confirmation that 2 sheets cover the 3 panels (incl. lattice waste) at drawing dimensions. | Fabricator + QS — at Detail Drawing sign-off
Low | Access equipment for 2.8 m height | Unsafe working or delay | Confirm existing ladder/scaffold on site or arrange hire. | Site supervisor — before install
Info | Lead time for CNC lattice + paint drying | Schedule slip beyond 2-week target | Written lead time from fabricator after colour & drawing OK. | Fabricator — after deposit & confirmations

## D. Calc Detail Basis
CALCULATION DETAIL / BASIS — Geometry + Cost Sheet Reconciliation
1. Panel Geometry (Drawing S71354-DET-01-C — still Geometry SoT)
Width each panel | 508 | mm | Drawing 508.0 (20")
Height Panel 1 | 1221 | mm
Height Panel 2 | 1858 | mm
Height Panel 3 | 2794 | mm
Total face area | 2.9835 | m² | ≈ 2.98 m²
Job Cost / Quotation area | 32.6 | sqft | 32.6 sqft ≈ 3.03 m² — consistent with drawing
2. PVC Quantity (locked to Job Cost)
Job Cost PVC 10 mm | 2 | sheets / pcs | C-3: SQFT 32.6, QTY 2 @ RM375 = RM750
Unit price locked | 375 | RM / sheet
Total PVC cost | 750 | RM
3. Paint Quantity (locked to Job Cost)
Job Cost Jotun Majestic | 4 | × 1 L | 2 (site) + 2 (panel) @ RM45 = RM180 total
Unit price locked | 45 | RM / 1 L
Total paint cost | 180 | RM
4. Supporting Materials (locked)
Masking Tape 2" Bundle | 1 | @ RM10 | Job Cost 31
X-Bond 500 ml | 1 | @ RM15 | Job Cost 32 — primary adhesive
Silicon Sealant (Paintable) | 0.5 | @ RM10 (costed) | Job Cost 34 — purchase 1 tube
Super Glue 10g Box | 0 | — not ordered | Job Cost 33 total RM0
5. Services (internal visibility)
Labour Installation | 300 | RM | Job Cost L summary
Transport | 300 | RM | Job Cost M summary
Commission 5% | 90 | RM | Job Cost P
Assumption / Reconciliation Notes
• Job Cost sheet is now the primary source for purchase quantities and unit prices. Drawing remains Geometry SoT for panel dimensions and preferred colour codes (SUN 1369 / OAK SAND 1987). • Cost sheet uses generic 'Color perlu di confirm' under Jotun Majestic — this is the single open TBC. • 2 sheets @ RM375 is accepted as the fabricator’s practical order qty for the 3 panels (higher reasonable quantity principle satisfied). • No invented dimensions. Super Glue explicitly zeroed.

## E. Drawing vs Site Assumptions
DRAWING-vs-SITE & ASSUMPTIONS TABLE (v2)
Source | Statement | BOM Impact | Status
Drawing S71354-DET-01-C | 10 mm THK PVC PANEL, JOTUN SUN 1369; WALL BASE JOTUN OAK SAND 1987 | Preferred colour codes retained as reference; cost sheet overrides to 'TBC Majestic' | Reference only — confirm
Job Cost 14-Sep-2026 | PVC 10 mm × 2 pcs @ RM375; Jotun Majestic 4 × 1 L @ RM45; X-Bond, Silicon, Masking Tape costed | Purchase qtys & unit prices locked | Active — primary
Job Cost / Quotation | Color perlu di confirm sblm pemasangan | Explicit High-severity TBC before paint order | Open
Drawing dimensions | 508 × 1221 / 1858 / 2794 mm | Used for area check; consistent with 32.6 sqft | Geometry SoT
Job Cost | Labour RM300 + Transport RM300 + Comm 5% RM90 | Internal COGS only; not re-ordered as materials | Internal
Assumption | 2 sheets sufficient for 3 CNC lattice panels incl. waste | If fabricator reports otherwise, adjust order | Labelled — confirm with fabricator
Site (pending) | Existing wall condition / substrate | Affects X-Bond performance & any mechanical backup | To be verified on site

## F. Local Supplier Directory
LOCAL SUPPLIER DIRECTORY — Puncak Alam / Shah Alam Hub (v2)
All entries from live web search. Phone only if explicitly found; otherwise NULL. Source URL for audit. Green = Local self-collect; Yellow = Regional.
Category | Business Name | WhatsApp / Contact | Address | Specialty | Logistics Note | Source URL
Hardware & Fasteners / Adhesives | Kasa Hardwares Sdn. Bhd. | 011-3721 0866 | No 1, Jalan Eko Perindustrian 5/3A, Eco Business Park V, 42300 Puncak Alam, Selangor | Hardware, tools, fasteners, adhesives, painting tools, X-Bond likely stocked | Local – Self-collect | https://www.malaysialistings.com/listings/kasa-hardwares-sdn-bhd-online-hardware-store-malaysia
Hardware & Fasteners / Adhesives | Puncak Alam Hardware Sdn Bhd | 03-3392 3919 / 012-685 1993 | Lot 1272, Batu 9, Jalan Puncak Alam, 42200 Kapar Klang, Selangor | Hardware, construction materials, adhesives | Local / near Puncak Alam – Self-collect | http://www.puncakalamhardware.com.my
Paint & Coatings | Yi Sheng Hardware & Timber Sdn. Bhd. (Jotun Flagship) | NULL (call store) | Lot 2794, Jln Sungai Buloh, Kampung Melayu Subang, 40150 Shah Alam, Selangor | Jotun authorised / flagship, Majestic range, colour tools | Regional – Requires transport from Shah Alam | https://www.facebook.com/jotunmalaysia/videos/jotun-showroom-at-yi-sheng-hardware-shah-alam/866130601421364/
Paint & Coatings | Jotun Paints (Malaysia) Sdn Bhd | 03-5123 5500 | Lot 7, Persiaran Perusahaan, Seksyen 23, 40300 Shah Alam, Selangor | Manufacturer / official | Regional – Shah Alam hub | https://mpcma.org.my/index.php/jotun-paints?ml=1
Paint & Coatings | Mr. Paint Shop (multiple outlets) | NULL (outlet dependent) | Shah Alam, Subang Jaya, Puchong, etc. | Authorised multi-brand incl. Jotun Majestic | Regional – nearest outlet | https://www.facebook.com/mrpaintshopmalaysia/
Boards & Timber / PVC | Rugaval Rubber Sdn Bhd | 03-5191 7961 / 03-5191 8961 | No. 26, Jalan Bagan Nara 26/8, Hicom Industrial Park, Seksyen 26, 40400 Shah Alam, Selangor | PVC rigid / foam sheet supplier | Regional – Shah Alam | https://www.syntheticrubberproducts.com.my
Custom / CNC | Local CNC / signage fabricators | NULL (quote required) | Selangor / KL factories | CNC cutting, PVC board fabrication | Regional – quote + delivery | Search 'CNC PVC panel Shah Alam' or package with sheet supplier
Legend: Green = Local (self-collect preferred). Yellow = Regional (transport planning required).
Search radius: Primary Puncak Alam → fallback Shah Alam / Klang Valley. X-Bond (X'traseal) widely available at hardware stores.

## G. BOM Change Log
BOM CHANGE LOG
Date | Agent / Step | What Changed | Why | Impact
2026-09-14 | Agent 1–6 (v1) | Initial BOM from Quotation Q260163 + Drawing S71354-DET-01-C | First pipeline run | Baseline quantities estimated
2026-09-15 | Agent 1 Intake (v2) | Ingested MATERIAL COST / Job Cost sheet 14-Sep-2026 | New primary cost & qty source | PVC 2 pcs, Paint 4×1L, X-Bond, Silicon, Masking Tape locked
2026-09-15 | Agent 2–3 Normalise + Calc | Reconciled drawing area 2.98 m² with Job Cost 32.6 sqft; adopted Job Cost unit prices | Cost sheet overrides previous estimates for purchase qty & price | Higher confidence on material lines
2026-09-15 | Agent 4 Reconciliation | Colour remains TBC (drawing codes vs cost sheet 'confirm'); Super Glue zeroed; labour/transport internal only | Highest reasonable + no silent guess | Only 1 High-severity TBC left
2026-09-15 | Agent 5 Verification | Confirmed X-Bond = X'traseal X'Bond; Jotun Majestic 1L market ~RM45 matches cost sheet | Primary sources | Prices validated
2026-09-15 | Agent 7 Sourcing | Re-confirmed local hardware (Kasa, Puncak Alam Hardware) + regional Jotun/PVC | No-hallucination rule | Directory unchanged, still valid
2026-09-15 | Agent 6 Export (v2) | Full workbook regenerated; Completeness 14/14; unit prices populated; internal COGS vs sell price shown | Cost sheet integrated | Ready for coordinator — colour confirm then order